18CE701

Hall Ticket Number:

| IV/IV B.Tech (Regular) DEGREE EXAMINATION |  |  |  |
| --- | --- | --- | --- |
| January, 2022 | Civil Engineering |  |  |
| Seventh Semester | Construction Management |  |  |
| Time: Three Hours |  | Maximum: 50 Marks |  |
| Answer Question No.1 compulsorily. |  |  | (1X10 = 10 Marks) |
| Answer ONE question from each unit. |  |  | (4X10=40 Marks) |

| 1. | a) | Define construction management. | CO1 |  |
| --- | --- | --- | --- | --- |
|  | b) | Write any two advantages of milestone charts over bar charts. | CO1 |  |
|  | c) | List out the methods of scheduling. | CO1 |  |
|  | d) | What is critical path? | CO2 |  |
|  | e) | Define EST. | CO2 |  |
|  | f) | What are the objectives of material management? | CO3 |  |
|  | g) | Name any two hoisting equipment. | CO3 |  |
|  | h) | What is TQM | CO4 |  |
|  | i) | What is documentation? | CO4 |  |
|  | j) | Define dummy activity. | CO4 |  |
| Unit -I |  |  |  |  |
| 2. | a) | What are the objectives and function of construction management? | CO1 | 5M |
|  | b) | For a construction project, the following activities are to be performed. - Activities P and Q can be performed in parallel - Activities R and S cannot start until P is complete - T cannot start until half work of activity R is completed. - Activity U can start only after activity S is completed. - Activity N succeeds activity R and - Activity W which is the last activity succeeds T. Draw the bar chart and determine the total completion time of the project. Activity; A; B; C; D; E; F; G; H. Duration (weeks); 2; 4; 2; 4; 6; 4; 5; 4. | CO1 | 5M |
| (OR) |  |  |  |  |
| 3. | a) | What are the methods of scheduling? Explain with the help of a suitable example, the method of preparing a bar chart. | CO1 | 5M |
|  | b) | Explain why planning is necessary. Describe various steps involved in it. | CO1 | 5M |
| Unit -II |  |  |  |  |
| 4. | a) | Differences between CPM and PERT. | CO2 | 5M |
|  | b) | Write the steps involved in optimization of cost. | CO2 | 5M |
| (OR) |  |  |  |  |
| 5. | a) | Write the advantages of network techniques over conventional techniques. | CO2 | 5M |
|  | b) | Write short note on Earliest expected time and Latest allowable occurrence time. | CO2 | 5M |
| Unit -III |  |  |  |  |
| 6. | a) | Discuss in detail the various factors affecting the cost of owning and operating the construction equipment. | CO3 | 5M |
|  | b) | Describe briefly about functions of material management department. | CO3 | 5M |
| (OR) |  |  |  |  |
| 7. | a) | What do you mean by resource smoothing? What are the steps involved in it? Explain briefly. | CO3 | 5M |
|  | b) | Name the equipment’s needed for compacting concrete and explain their uses in detail. | CO3 | 5M |
| Unit -IV |  |  |  |  |
| 8. |  | Discuss in detail about the quality assurance techniques. | CO4 | 10M |
| (OR) |  |  |  |  |
| 9. | a) | Enumerate the benefits of safety to employers, employees and customers. | CO4 | 5M |
|  | b) | Explain about the accident prevention program in construction site. | CO4 | 5M |