18MED34

Hall Ticket Number:

| IV/IV B.Tech (Regular) DEGREE EXAMINATION |  |  |  |
| --- | --- | --- | --- |
| January, 2022 | Mechanical Engineering |  |  |
| Seventh Semester | PROJECT MANAGEMENT |  |  |
| Time: Three Hours |  | Maximum: 50 Marks |  |
| Answer Question No.1 compulsorily. |  |  | (10X1 = 10 Marks) |
| Answer ONE question from each unit. |  |  | (4X10=40 Marks) |

| 1. | a) | Define project management | CO1 |  |
| --- | --- | --- | --- | --- |
|  | b) | What is quantifiable project | CO1 |  |
|  | c) | What is conceptualization in project life cycle | CO1 |  |
|  | d) | Difference between node and event | CO2 |  |
|  | e) | Define Qualitative risk analysis | CO2 |  |
|  | f) | What is crashing | CO2 |  |
|  | g) | Latest start time | CO2 |  |
|  | h) | How a project is controlled | CO3 |  |
|  | i) | Factors influencing Leadership Style | CO3 |  |
|  | j) | Types of project organization | CO3 |  |
| Unit -I |  |  |  |  |
| 2. | a) | Explain why project management is important in an organization. | CO1 | 5M |
|  | b) | Briefly discuss about the classification of projects | CO1 | 5M |
| (OR) |  |  |  |  |
| 3. | a) | Develop a WBS for a project in which you are going to build a personal computer. | CO1 | 5M |
|  | b) | Explain project life cycle process with a suitable diagram | CO1 | 5M |
| Unit -II |  |  |  |  |
| 4. | a) | Explain the Project Risk Analysis and Management (PRAM) process. | CO2 | 5M |
|  | b) | Differentiate CPM and PERT | CO2 | 5M |
| (OR) |  |  |  |  |
| 5. |  | A small project is composed of 7 activities whose time estimates are listed in the table below. Activity; Estimated duration (weeks). Optimistic; Most likely; Pessimistic. 1-2; 1; 1; 7. 1-3; 1; 4; 7. 1-4; 2; 2; 8. 2-5; 1; 1; 1. 3-5; 2; 5; 14. 4-6; 2; 5; 8. 5-6; 3; 6; 15. - Find the expected duration and variance for each activity. - Calculate the project duration time | CO2 | 10M |
| Unit -III |  |  |  |  |
| 6. | a) | Describe scheduling resources | CO3 | 5M |
|  | b) | Explain estimation techniques in cost management. | CO3 | 5M |
| (OR) |  |  |  |  |
| 7. | a) | How do we measure project progress and performance? | CO3 | 5M |
|  | b) | What are the different types of cost in project? | CO3 | 5M |
| Unit -IV |  |  |  |  |
| 8 | a) | Briefly discuss the key elements of organizational structure. | CO4 | 5M |
|  | b) | Explain any two types of leadership styles. | CO4 | 5M |
| (OR) |  |  |  |  |
| 9. | a) | Explain briefly the characteristics of effective project teams | CO4 | 5M |
|  | b) | Discuss the levels of Project Management Maturity Model | CO4 | 5M |